Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 25 September 2026 |
| --- | --- |
| Team ID | SWTID-2026-2773 |
| Project Name | AI StudyBuddy |
| Maximum Marks |  |

1. Product Backlog, Sprint Schedule, and Estimation (4 Marks)

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Authentication | USN-1 | As a user, I can register with name, email, password and role. | 3 | High | [Member Name] |
| Sprint-1 | Authentication | USN-2 | As a user, I can log in with email and password. | 2 | High | [Member Name] |
| Sprint-1 | Authentication | USN-3 | As a user, I can refresh my token and log out. | 2 | Medium | [Member Name] |
| Sprint-1 | Materials | USN-4 | As a user, I can upload a .txt, .md or .pdf study material. | 3 | High | [Member Name] |
| Sprint-2 | Materials | USN-5 | As a user, I can list, view and delete my study materials. | 3 | High | [Member Name] |
| Sprint-2 | AI Learning | USN-6 | As a user, I can generate an AI summary. | 3 | High | [Member Name] |
| Sprint-2 | AI Learning | USN-7 | As a user, I can generate flashcards. | 3 | High | [Member Name] |
| Sprint-3 | AI Learning | USN-8 | As a user, I can generate an MCQ quiz. | 3 | High | [Member Name] |
| Sprint-3 | AI Learning | USN-9 | As a user, I can generate a personalized study plan. | 3 | High | [Member Name] |
| Sprint-3 | Admin | USN-10 | As an admin, I can manage users and view statistics. | 3 | Medium | [Member Name] |

2. Project Tracker, Velocity & Burndown Chart (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 10 | 6 Days | 22 Sep 2026 | 27 Sep 2026 | 10 | 27 Sep 2026 |
| Sprint-2 | 9 | 6 Days | 28 Sep 2026 | 03 Oct 2026 | 9 | 03 Oct 2026 |
| Sprint-3 | 9 | 6 Days | 05 Oct 2026 | 10 Oct 2026 | 9 | 10 Oct 2026 |

3. Velocity Calculation & Metrics

Team Velocity Calculations

- Total Completed Story Points: 10+9+9=28 Story Points

- Total Project Duration: 6+6+6=18 Days

- Average Team Velocity per Sprint:

Average Velocity per Sprint=Total Story PointsNumber of Sprints=283≈9.33 Story Points / Sprint

- Average Velocity per Iteration Unit (Story Points / Day):

Average Velocity (AV)=Total Completed Story PointsTotal Days=2818≈1.56 Story Points / Day

4. Visualizations (Burndown Chart & Velocity Chart)

AI StudyBuddy - Sprint Burndown Chart

A Burndown Chart visualizes the work remaining (28 Story Points down to 0) across the 18 days of project development.

AI StudyBuddy - Sprint Velocity Chart

The Velocity Chart illustrates the distribution of completed story points across Sprint 1 (10 SP), Sprint 2 (9 SP), and Sprint 3 (9 SP).

5. Reference Links

- https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

- https://www.atlassian.com/agile/tutorials/burndown-charts

- https://www.atlassian.com/agile/project-management

- https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

- https://www.atlassian.com/agile/tutorials/epics

- https://www.atlassian.com/agile/tutorials/sprints

- https://www.atlassian.com/agile/project-management/estimation